## Iteration 1
CS Capstone Task Tracker It. 1
Real Time Network Visualization Team

T-#	Tasks	Due Date	Distribution Info	Status	Remarks		Key
1.00	Poole - Project Timeline	COB 19-Mar-10	Capstone Class	Complete	Timeline for on time completion of the assigned project		Not Started	Stop
2.00	XML Documentation	22 – Mar – 10	Capstone Class & Mon. Meeting	Complete	XML Format for Front end team - Need format for Node Detection		In Progress	Working
3.00	Software Installation	24 – Mar – 10	Mon. Meeting	Complete	Installation of Snort, tcpdump, etc		Complete	Complete
4.00	Lockwood - Simple Log Parsing	25 – Mar – 10	Capstone Class	Working	Pull Ips, simple attack tags from logs		On-Hold	Standby
5.00	Jackson - XML outputting	26 - Mar - 10	Class	Complete	Convert Parse output to XML
6.00	King - Documentation	-		Complete	Compile SRS info, pamphlet form
7.00				Stop
8.00				Stop
9.00				Stop
10.00				Stop
11.00				Stop
12.00				Stop
13.00				Stop
14.00				Stop
15.00				Stop

## Iteration 2
CS Capstone Task Tracker It. 2
Real Time Network Visualization Team

T-#	Tasks	Due Date	Distribution Info	Status	Remarks		Key
1.00	XML Documentation, Node detection	29-Mar-10	King	Complete	Establish XML format, send to front-end and Daniel Sawyer		Not Started	Stop
2.00	Traffic Monitor - Manipulating Snort Rules	30-Mar-10	Rollins, Lockwood	Complete	Learn how to add/modify Snort rules and what it picks up by default		In Progress	Working
3.00	Node detection - Input config	30-Mar-10	King	Complete	Complete Config file and IP address input		Complete	Complete
4.00	XML Generation, Node detection	31-Mar-10	Jackson	Complete	Generate XML from my Node detection output		On-Hold	Standby
5.00	Node detection - Basic Complete	2-Apr-10	King	Working	1st Revision of Node detection, should have all basic functionality
6.00	Traffic Monitor - 1st Revision	2-Apr-10	Rollins, Lockwood	Working	1st Revision of Traffic Monitor, parse snort logs, generate needed output, basic attack types
7.00				Stop
8.00				Stop
9.00				Stop
10.00				Stop
11.00				Stop
12.00				Stop
13.00				Stop
14.00				Stop
15.00				Stop

## Iteration 3
CS Capstone Task Tracker It. 3
Real Time Network Visualization Team

T-#	Tasks	Due Date	Distribution Info	Status	Remarks		Key
1.00	Testing Node detection on router	7-Apr-10	King	Complete	Need to get access to router to test node detection		Not Started	Stop
2.00	Test pingsweeping vs. ARP cache	7-Apr-10	King	Complete	Check time of pingsweeping for active node detection		In Progress	Working
3.00	Stat tracking tools	7-Apr-10	Rollins	Complete	Establish method to be used for stat tracking		Complete	Complete
4.00	Attack Detection XML fix	7-Apr-10	Jackson, Lockwood	Complete	Fix the XML generator for Attack Detection to reflect the full output of the program		On-Hold	Standby
5.00	Debugging node Detection	9-Apr-10	King	Complete	Fix bugs in node detection. Correct problems in bash coding.
6.00	Research new rules for attack detection	9-Apr-10	Lockwood	Complete	Find ways to track new attack types
7.00	Stat tracking crude implementation	9-Apr-10	Rollins	Complete	Get a basic stat tracking system running
8.00	SRS update	9-Apr-10	Jackson, King	Working	Bring SRS up to date
9.00				Stop
10.00				Stop
11.00				Stop
12.00				Stop
13.00				Stop
14.00				Stop
15.00				Stop

## Iteration 4
CS Capstone Task Tracker It. 4
Real Time Network Visualization Team

T-#	Tasks	Due Date	Distribution Info	Status	Remarks		Key
1.00	Node Detection – Add Caching	12-Apr-10	King	Complete	Rough Implementation of OS Caching		Not Started	Stop
2.00	Generate Logfiles	13-Apr-10	Extras	Complete	Generate snort log files for Lockwood		In Progress	Working
3.00	Installation on router	13-Apr-10	King, Lockwood, Sawyer	Complete	Install and configure software on new router		Complete	Complete
4.00	Prepare Production Test	14-Apr-10	All team	Complete	Fix bugs, implement automation, prepare Production test for review in class 4/9		On-Hold	Standby
5.00	Review Production Test Results	16-Apr-10	King	Working	Review results of Production test for completeness and prepare revisions and fixes for team
6.00	Bug fixes for next Review	19-Apr-10	All team	Working	Make changes and fix bugs to push a final revision
7.00	Develop new rules for Snort	16-Apr-10	Lockwood, Extras	Working	Using new logfiles, develop more rules for attack detection

9.00				Stop
10.00				Stop
11.00				Stop
12.00				Stop
13.00				Stop
14.00				Stop
15.00				Stop